## Summary
SUMMARY OF YOUTH CENTER REFURBISHMENT
Straightening of internal protection fence | 0
General painting of whole compound | 0
Grand total | 0

## Straightening protection
Straightening of internal protection fence
S.n. | Description of activities | Unit | QTY | Rate in USD | Amount in USD
A-1000 | PCC over lintel wall
A-1001 | Repair of approximately 50m length, 500mm width and 400mm thick of the broken part of existing lintel wall using masonry stone wall laying and connecting with cement sand mortar of 1:6 mixing ratio. Note that the wall should be kept moist and protected from the sun for at least 10days | m³ | 10 |  | 0
A-1002 | Construction of 500mm width 100mm height plain cement concrete of 1:3:6 mixing ratio over the existing lintel wall at surrounding area of football playground. Note that the wall should be kept moist and protected from the sun for at least 10days. | m³ | 17.5 |  | 0
Sub total A |  |  |  |  | 0
B-2000 | Iron bars to hold the existing weak plastic covered mesh
B-2001 | Provide and fixing of 4 longitudinal lines of iron bars of diameter Ø 8mm inside the 4 small holes on the concrete poles at surrounding area of the football playground. If the existing small holes doesn’t align, the vendor should open a new aligned hole using drilling machine without damaging the concrete pole. N.B. Note the price will be include providing of the iron bars, welding with electrodes and drill new holes id it is necessary. | m | 1540 |  | 0
Sub total A |  |  |  |  | 0
C-3000 | Removing of existing two pedestrain doors
C-3001 | Remove broken and malfunctioning two pedestrian access steel grilled door of 2,450mm x 2,200mm height to the football playground. After providing and fixing of new steel grilled doors made with external frame of GI pipes of diameter Ø 5mm welded on it with GI chicken mesh of rhomboid shape with at least three side bolt locks. The door should apply with three coats of anti-rust paint. | Item | 2 |  | 0
Sub total A |  |  |  |  | 0
0

## General painting
General painting of whole compound
A-1000 | Coaching rooms
A-1001 | Apply first coat whitewash paint on internal and external walls surfaces consists of: a). One coat of white PRIMER painting coat; b). Apply with filler FOXNITE WATER RESISTENTE FINE FINSH powder. Note that during the price will be include fine sandpaper in order to get smooth surfaces and roller to reach the high places. | m² | 236.176 | 0
A-1002 | Apply second coat washable paint on internal wall surfaces which consists of a). One coat of white/colored PRIMER painting; b). One coat of National type "EGGSHELL EMULSION (SILK FINISH) paints. Note that price will be include roller to reach the height places. | m² | 236.176 | 0
Sub total A |  |  |  | 0
Two twin toilets
| Apply first coat whitewash paint on internal and external walls surfaces consists of: a). One coat of white PRIMER painting coat; b). Apply with filler FOXNITE WATER RESISTENTE FINE FINSH powder. Note that during the price will be include fine sandpaper in order to get smooth surfaces and roller to reach the high places. | m² | 60.74 | 0
Sub total A |  |  |  | 0
Fence of playground
| Apply first coat whitewash paint on internal and external walls surfaces consists of: a). One coat of white PRIMER painting coat; b). Apply with filler FOXNITE WATER RESISTENTE FINE FINSH powder. Note that during the price will be include fine sandpaper in order to get smooth surfaces and roller to reach the high places. | m² | 2312 | 0
Sub total A |  |  |  | 0
Mosque
| Apply first coat whitewash paint on internal and external walls surfaces consists of: a). One coat of white PRIMER painting coat; b). Apply with filler FOXNITE WATER RESISTENTE FINE FINSH powder. Note that during the price will be include fine sandpaper in order to get smooth surfaces and roller to reach the high places. | m² | 281.6 | 0
| Apply second coat washable paint on internal wall surfaces which consists of a). One coat of white/colored PRIMER painting; b). One coat of National type "EGGSHELL EMULSION (SILK FINISH) paints. Note that price will be include roller to reach the height places. | m² | 281.6 | 0
Sub total A |  |  |  | 0
Two ticket issue rooms
| Apply first coat whitewash paint on internal and external walls surfaces consists of: a). One coat of white PRIMER painting coat; b). Apply with filler FOXNITE WATER RESISTENTE FINE FINSH powder. Note that during the price will be include fine sandpaper in order to get smooth surfaces and roller to reach the high places. | m² | 60 | 0
Sub total A |  |  |  | 0
Steel structure doors and gates
| Apply three coats gloss paint on internal external steel structure surfaces such as two main entrance gates, handrail of VIP sitting stages, steel doors etc. | Items | 1 | 0
Sub total A |  |  |  | 0
0